EXECUTION COMMAND

Commercial Proof Run 001

The 90-day command that turns the institution from architecture into customer-backed authority.

# Command intent

MISSION Prove one premium GoalOS product with three unrelated customers, one repeated delivery path, one independent verdict, one recurring expansion, one transferable capability and zero material trust breaches.

# The frozen commercial wedge

| Element | Frozen decision |
| --- | --- |
| Ideal buyer | Board, CEO, CIO, CISO, AI leader, investor or strategic buyer facing a consequential AI decision |
| Customer question | Should we deploy, acquire, scale, continue funding, narrow, repair or stop this AI initiative? |
| Product | GoalOS Enterprise Proof Mission |
| Founding price | $250,000 standard; scope may be reduced rather than price discounted |
| Delivery window | 15 business days after data readiness |
| Output | Mission Contract, Proof Debt, AGI Jobs, Evidence Docket, independent verdict, governed decision and action plan |
| Expansion | GoalOS Proof Office at $1,000,000 per year |
| Rights | Network-admissible base; customer-private and exclusive rights priced at a premium |

# Days 1-14 - freeze and activate

Ratify the Charter of Productive Intelligence and the public claim boundary.

Freeze one customer profile, one decision question, one price, one scope, one Evidence Docket and one acceptance path.

Configure the autonomous deal room, contract library, payment path, data boundary and consent ledger.

Recruit at least two independent reviewers with no economic incentive to issue PASS.

Construct the first 60-account list and launch the permissioned MasterClass / briefing sequence.

Run an internal GoalOS Sells GoalOS rehearsal with complete cost and intervention capture.

# Days 15-45 - close and execute

Close three unrelated paying customers under substantially identical terms.

Collect 50% at signature, 30% at frozen Evidence Docket and 20% at defined acceptance or terminal decision.

Execute real AGI Jobs with observable tools, budgets, deadlines, evidence and recovery states.

Record every retry, failure, human intervention, external cost and unsupported claim.

Publish no customer claim before customer authorization and independent review.

# Days 46-75 - verify and productize

Deliver three Evidence Dockets and at least one independently reviewed verdict.

Identify one repeated method that qualifies as a candidate Validated Skill.

Freeze a fresh successor test before the candidate is permitted to influence the new mission.

Convert accepted customers into evidence-based Proof Office proposals.

Measure contribution margin, customer value, reviewer burden, replay and founder intervention.

# Days 76-90 - admit, repeat or stop

Issue Chronicle decisions: admit, condition, repair, reject, quarantine, supersede or retire.

Run the fresh Generation 2 comparison and independent review.

Activate at least one recurring Proof Office or repeat mission.

Publish one public-safe customer-authorized Proof Docket.

Authorize the next capital gate only if commercial, trust, capability and economics thresholds pass.

# Command dashboard

| Gate | Target | Stop / repair condition |
| --- | --- | --- |
| Paying customers | 3 | Fewer than 3 after 60 qualified accounts and 90 days |
| Mission repeatability | 3 similar missions | Delivery remains materially bespoke or founder-dependent |
| Independent authority | At least 1 reviewed outcome | No separated reviewer route or incomplete evidence |
| Retention | At least 1 repeat / expansion | No customer continues after accepted delivery |
| Contribution | Positive | Variable cost, refund, support or claims burden destroys margin |
| Capability | At least 1 rights-cleared skill | No fresh transfer or rights block reuse |
| Successor | At least 1 measured improvement | No preregistered metric improves under equal or harder constraints |
| Trust | 0 material breaches | Security, privacy, claim or authorization incident |

# Capital ceiling

| Use | 90-day ceiling |
| --- | --- |
| Product and autonomous commercial lane | $100,000 |
| Evidence, evaluator and specialist operations | $50,000 |
| Security, legal, privacy and contracts | $50,000 |
| Category launch and qualified demand | $35,000 |
| Contingency | $15,000 |
| Total | $250,000 |

FINANCING LAW No capital is released to the next stage merely because the architecture is attractive. Each tranche retires a distinct class of Proof Debt.

# The final command

Build the category now. Sell the bounded mission now. Publish the evidence. Compound only what passes.

# Selected sources and evidence boundary

External sources establish the timing context. GoalOS pricing, revenue, ROI, financing, valuation and capacity scenarios are management hypotheses until verified by customer and operating evidence.

OpenAI - ChatGPT Work and workspace agents

OpenAI - Agents SDK and long-running work

METR - Task-Completion Time Horizons

Google DeepMind - AlphaEvolve impact

Google DeepMind - From AGI to ASI

Anthropic Institute - Research agenda

Gartner - Worldwide AI spending forecast

Government of Canada - Sovereign AI supercomputing initiative

MONTREAL.AI - Merkle Roots for the Validated Skill Graph

MONTREAL.AI - Private On-Chain Validated Skill Graph

CLAIM BOUNDARY This document does not claim achieved general intelligence, unrestricted recursive improvement, guaranteed customer outcomes, legal certification, audited forecasts, or a present enterprise valuation. The governing doctrine is maximum ambition with minimum unsupported claim.